CoffeeManager-OS

Project Roadmap & Implementation Plan

Hybrid Agent Architecture  —  Python + OpenClaw

Version 1.0 · May 2026

Prepared for: Coffee Shop Owner / Operations Lead

# Executive Summary

CoffeeManager-OS is a hybrid autonomous operations agent purpose-built for a high-volume specialty coffee shop in Lithuania. It combines deterministic Python logic for all financial calculations with the OpenClaw agentic brain for non-deterministic tasks such as government portal navigation, OCR receipt processing, and staff compliance workflows.

This document defines the full implementation roadmap across five phases, from environment setup through to production deployment and ongoing optimisation. The total estimated build time is 14–18 weeks for a solo developer or 8–10 weeks with a two-person team.

Key Principle Python handles all arithmetic and data formatting. OpenClaw handles all judgment, navigation, and document understanding. These two concerns never cross.

## Project Goals

- Full VMI i.EKA / i.SAF compliance with zero manual data entry

- Sodra new-hire registration drafted within 60 seconds of detection

- Daily Z-report audit running autonomously at 07:00 every morning

- Inventory reorder triggered automatically when stock falls below safety threshold

- 100% human-in-the-loop on all tax submissions and employee registrations

## Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Deterministic core | Python 3.11+ | VAT logic, P&L, inventory, i.SAF XML |
| Agentic brain | OpenClaw | Portal navigation, OCR, HR forms |
| OCR engine | docTR / EasyOCR | Receipt and invoice scanning |
| Database | SQLite (WAL mode) | Audit log, portal actions, notifications |
| Web framework | FastAPI | Dashboard, webhooks, POS integration |
| Notifications | Telegram Bot API | Owner alerts, HITL confirmations |
| POS connector | Paysera / RoboLabs API | Sales data, Z-report extraction |

| Phase 1 Environment & Foundation | Weeks 1–2 |
| --- | --- |

Set up the full development environment, project structure, database schema, and configuration management before writing any business logic. A clean foundation here prevents rework in every subsequent phase.

### Step-by-step tasks

- Create the project directory structure (core/, agent/, data/, config/, skills/)

- Initialise a Python 3.11+ virtual environment and pin all dependencies in requirements.txt

- Install Node.js for any docx generation scripts; confirm npm package availability

- Run migrate.py to initialise memory.sqlite with all four schema migrations

- Create config/settings.env with placeholders for all required credentials

- Register a Telegram Bot via @BotFather; obtain BOT_TOKEN and CHAT_ID

- Obtain OpenClaw API key from the OpenClaw dashboard

- Confirm POS API credentials (Paysera or RoboLabs) and test a sample Z-report pull

- Write and run a smoke-test script that reads from SQLite, sends a Telegram message, and calls the POS API

- Commit the skeleton to version control with a .gitignore excluding config/ and data/

### Deliverables

| Task | Owner | Effort | Dependency |
| --- | --- | --- | --- |
| Project scaffold created | Developer | 2 hrs | — |
| migrate.py executed successfully | Developer | 1 hr | Scaffold |
| Telegram bot live and tested | Developer | 1 hr | Credentials |
| POS API smoke test passing | Developer | 2 hrs | POS credentials |
| Environment smoke test green | Developer | 1 hr | All above |

Risk POS API documentation for Lithuanian providers (Paysera/RoboLabs) can be sparse. Budget an extra day if test credentials are not immediately available.

| Phase 2 Python Deterministic Core | Weeks 3–5 |
| --- | --- |

Build and test all deterministic Python modules. These must be correct before the OpenClaw agent is introduced, because the agent trusts Python output completely and never re-validates it.

### Step-by-step tasks

- Implement core/accounting.py: Decimal-based PVM calculation (21% standard, 9% reduced), Z-report audit logic, and run_daily_audit() returning a typed dict

- Implement core/inventory.py: check_stock_levels() pulling from POS API and comparing against configurable safety-stock thresholds

- Implement core/integrations/paysera.py (or robolabs.py): authenticated API client with retry logic and structured response models

- Implement core/isaf_generator.py: build_isaf_xml() producing valid i.SAF XML validated against the official VMI XSD schema file

- Download the official VMI i.SAF XSD from the VMI developer portal and add to config/schemas/isaf.xsd

- Write unit tests for every function in core/ using pytest; target 100% coverage on accounting.py

- Implement migrate helper functions: log_audit(), log_portal_action(), notify_if_new()

- Add a CLI test runner: python -m core.accounting --test to verify Z-report logic against fixtures

### Deliverables

| Task | Owner | Effort | Dependency |
| --- | --- | --- | --- |
| accounting.py with full PVM logic | Developer | 1 day | — |
| inventory.py with API integration | Developer | 1 day | POS API |
| isaf_generator.py + XSD validation | Developer | 2 days | VMI XSD |
| pytest suite, all tests green | Developer | 1 day | All above |
| migrate helpers integrated | Developer | 0.5 day | migrate.py |

Critical Rule Never use float arithmetic for any monetary value. All amounts must use Python's Decimal type with ROUND_HALF_UP. A single float rounding error in a tax filing can trigger a VMI audit.

| Phase 3 OpenClaw Agent Brain | Weeks 6–9 |
| --- | --- |

Implement the OpenClaw agentic layer: the soul.md system prompt, all skill files, and the agent runner that bridges Python context to OpenClaw tasks. This phase ends with the full hybrid loop running end-to-end in a staging environment.

### Step-by-step tasks

- Write agent/soul.md: full identity, tool manifest, protocol definitions for Daily Audit, Receipt Processing, New Hire, and Inventory tasks

- Implement agent/runner.py: OpenClawAgent class with run_task() dispatcher, session ID management, and structured result returns

- Implement skills/scan_receipt.py: docTR OCR pipeline, field extraction (VAT code, company code, date, amounts, PVM code), confidence scoring

- Implement skills/vmi_submit.md: step-by-step OpenClaw instructions for navigating imas.vmi.lt, populating the i.SAF draft form, and saving without submitting

- Implement skills/sodra_draft.md: OpenClaw instructions for draudejai.sodra.lt, 1-SD form population, and 24-hour advance-notice date enforcement

- Implement main.py: full bootstrap sequence, Phase 1 Python core, Phase 2 OpenClaw dispatch, send_telegram() with deduplication

- Wire notify_if_new() into every alert path: AUDIT_MISMATCH, STOCK_LOW, RECEIPT_READY, NEW_HIRE

- Test the full hybrid loop end-to-end with a dummy receipt image and a dummy shift CSV entry in a staging environment with test credentials

- Validate that no tax form or Sodra submission fires without Telegram confirmation

### Deliverables

| Task | Owner | Effort | Dependency |
| --- | --- | --- | --- |
| soul.md finalised and reviewed | Developer + Owner | 1 day | — |
| agent/runner.py with full dispatcher | Developer | 2 days | soul.md |
| scan_receipt.py OCR pipeline | Developer | 2 days | docTR install |
| vmi_submit.md skill tested on portal | Developer | 2 days | VMI test account |
| sodra_draft.md skill tested on portal | Developer | 1 day | Sodra test account |
| main.py full loop, end-to-end test | Developer | 1 day | All above |

Security Note VMI and Sodra credentials must never appear in soul.md or any skill file. All credentials are read from environment variables at runtime. OpenClaw receives only session tokens, not raw passwords.

| Phase 4 FastAPI Dashboard & Hardening | Weeks 10–12 |
| --- | --- |

Add a lightweight FastAPI web dashboard for the owner, implement the POS webhook receiver, harden error handling across all modules, and perform a full compliance review before production.

### Step-by-step tasks

- Set up FastAPI app in api/main.py with endpoints: GET /status (last audit result), GET /receipts (processing queue), POST /webhook/pos (POS event receiver), POST /confirm/{event_key} (owner HITL confirmation)

- Implement the /confirm/{event_key} endpoint to mark notifications_sent.acknowledged_at and trigger the next agentic step

- Add APScheduler (or similar) for the 07:00 daily audit cron and the Sunday inventory check

- Implement comprehensive error handling: every external API call and every OpenClaw task wrapped in try/except with structured error logging to portal_actions

- Add circuit-breaker logic for VMI portal interactions: if three consecutive portal_actions show outcome=failure for the same portal, pause and alert the owner instead of retrying endlessly

- Conduct a full compliance review: verify i.SAF XML validates against current VMI XSD, verify all Sodra 1-SD fields match current form version, verify all Telegram messages include required human-confirmation language

- Write integration tests covering: audit mismatch detection, receipt OCR-to-draft pipeline, new hire detection-to-Sodra-draft flow

- Deploy to a staging server (VPS or Raspberry Pi on-site) and run for one full week against live POS data with real receipts

### Deliverables

| Task | Owner | Effort | Dependency |
| --- | --- | --- | --- |
| FastAPI dashboard with all endpoints | Developer | 3 days | Phase 3 complete |
| Cron scheduler configured | Developer | 0.5 day | FastAPI |
| Circuit breaker for portal failures | Developer | 1 day | runner.py |
| Compliance review sign-off | Developer + Owner | 1 day | All modules |
| Integration test suite green | Developer | 1 day | All above |
| One-week staging run completed | Developer + Owner | 1 week | Staging deploy |

Go / No-Go Gate Do not proceed to Phase 5 until the staging run completes with: zero unhandled exceptions in portal_actions, zero unsolicited VMI or Sodra submissions, and owner confirmation that all Telegram alerts are accurate.

| Phase 5 Production Launch & Optimisation | Weeks 13–18 |
| --- | --- |

Deploy to production, train the owner on the HITL confirmation workflow, and implement the optional enhancement modules (predictive scheduling, waste analytics, machine self-diagnosis) as the system stabilises.

### Step-by-step tasks

- Switch all environment variables from staging to production credentials

- Run migrate.py on the production database to initialise the live schema

- Deploy the FastAPI app behind a reverse proxy (nginx) with HTTPS and basic auth on the dashboard

- Run the first live daily audit at 07:00 and verify Telegram output with the owner present

- Train the owner on the HITL workflow: what each Telegram message means, how to confirm via the /confirm endpoint or Telegram reply, what to do if a message does not arrive

- Monitor portal_actions and audit_log daily for the first two weeks; review with the owner each Friday

- After two stable weeks, begin Phase 5 enhancements in order of ROI: (1) predictive labor scheduling, (2) supply chain waste analytics per barista, (3) customer sentiment loop, (4) machine self-diagnosis

- Schedule a monthly review: check VMI XSD for schema updates, check Sodra portal for 1-SD form version changes, update skill files accordingly

### Enhancement modules — priority order

| # | Module | Est. effort | Primary benefit |
| --- | --- | --- | --- |
| 1 | Predictive labor scheduling | 1–2 weeks | Reduce labor cost by 5–10% |
| 2 | Waste analytics per barista | 1 week | Identify over-pouring; cut COGS |
| 3 | Customer sentiment loop | 1 week | Win-back lapsed customers |
| 4 | Machine self-diagnosis | 2–3 weeks | Prevent rush-hour breakdowns |

# Risk Register

The following risks are ranked by likelihood. All mitigations are built into the implementation plan above.

| Risk | Impact | Mitigation |
| --- | --- | --- |
| VMI portal UI changes breaking skill files | High | Monthly skill file review; screenshot-based regression test saved per session |
| i.SAF XML schema update by VMI | High | XSD pinned in config/; automated schema diff check in CI pipeline |
| Sodra 1-SD form version change | High | Monthly compliance review step in Phase 5 checklist |
| POS API downtime during audit window | Medium | Retry with exponential backoff; alert owner if 3 retries fail |
| OCR confidence below threshold on messy receipts | Medium | Confidence score gate: receipts below 80% flagged for manual review |
| Telegram bot token expiry or rate limit | Low | Token refresh documented in runbook; fallback email alert configured |

# Timeline Summary

| Phase | Name | Weeks (solo) | Weeks (2-person) | Key output |
| --- | --- | --- | --- | --- |
| 1 | Environment & Foundation | 1–2 | 1 | Running smoke tests |
| 2 | Python Deterministic Core | 3–5 | 2–3 | pytest suite green |
| 3 | OpenClaw Agent Brain | 6–9 | 4–6 | End-to-end hybrid loop |
| 4 | Dashboard & Hardening | 10–12 | 7–8 | Staging run complete |
| 5 | Production & Optimisation | 13–18 | 9–10 | Live + enhancements |

Final Note The HITL constraint — never submit a VMI filing or Sodra registration autonomously — is non-negotiable at every phase. Every release must be tested specifically for the absence of autonomous submission before being promoted to production.